## Sheet1
No | Task | Task Status | Date of Sprint
|  |  | Start date | Expectation date | Date of completion
1 | Preprocessing Data
| Augmentasi data | Completed | 2023-11-18 | 2023-11-18 | 2023-11-18
| Pembagian dataset | Completed | 2023-11-18 | 2023-11-18 | 2023-11-18
2 | Pembangunan Model
| Pemilihan model | Completed | 2023-11-27 | 2023-11-27 | 2023-11-27
| Pelatihan model | Completed | 2023-11-27 | 2023-11-27 | 2023-11-27
| Evaluasi kinerja model | Completed | 2023-11-27 | 2023-11-27 | 2023-11-27
3 | Validasi Model
| Pengujian pada test set | Completed | 2023-11-27 | 2023-11-27 | 2023-11-27
| Analisis hasil dan nilai akurasi | Completed | 2023-11-27 | 2023-11-27 | 2023-11-27
4 | Deploy Web
| Front End web | Completed | 2023-12-11 | 2023-12-11 | 2023-12-11
| Back End web | Completed | 2023-12-11 | 2023-12-11 | 2023-12-11
| Testing | Completed | 2023-12-11 | 2023-12-11 | 2023-12-11